## Sheet1
| Project name: | Online Voting System Using Blockchain |  |  | Project name: | Online Voting System Using Blockchain
| Project Start: | 2024-07-11 |  |  | Project Start: | 2024-07-11
| Current Date: | 2025-04-07 |  |  | Current Date: | 2024-10-16
| Weeks in Progress: | 39 |  |  | Weeks in Progress: | 14
[9 empty] | 2024-07-11 | 2024-07-18 | 2024-07-25 | 2024-08-01 | 2024-08-08 | 2024-08-15 | 2024-08-22 | 2024-08-29 | 2024-09-05 | 2024-09-12 | 2024-09-19 | 2024-09-26 | 2024-10-03 | 2024-10-10 | 2024-10-17
Task | Start Date | End Date | Days | Progress | Start Date | End Date | Days | Progress | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Group Finalization / Domain | 2024-07-11 | 2024-07-17 | 6 | 100% | 2024-07-11 | 2024-07-17 | 6 | 100%
Topic finalization/Project Name submission (objectives/problem statement/scope) | 2024-07-18 | 2024-07-24 | 6 | 100% | 2024-07-18 | 2024-07-24 | 6 | 100%
Topic finalization/Project Name submission | 2024-07-25 | 2024-07-31 | 6 | 100% | 2024-07-25 | 2024-07-31 | 6 | 100%
Literature study and limitation of existing system (refer IEEE/ACM/Springer/Elsevier journal papers) | 2024-08-01 | 2024-08-07 | 6 | 80% | 2024-08-01 | 2024-08-07 | 6 | 100%
Abstract, Problem statement/scope and objective Finalization. | 2024-08-08 | 2024-08-14 | 6 | 90% | 2024-08-08 | 2024-08-14 | 6 | 100%
Implementation plan /Timeline chart for sem vii and viii | 2024-08-15 | 2024-08-21 | 6 | 50% | 2024-08-15 | 2024-08-21 | 6 | 100%
SRS-Functional and Non functional requirements, S/w Engg Model | 2024-08-22 | 2024-08-28 | 6 | 0% | 2024-08-22 | 2024-08-28 | 6 | 100%
Proposed system architecture/flow chart and Analysis and Design: Use Case, DFD-0,Sequence | 2024-08-29 | 2024-09-04 | 6 | 0% | 2024-08-29 | 2024-09-04 | 6 | 100%
Review I(on Activity 3 to 8)
Reviw Paper Publication (Survey Paper) | 2024-09-05 | 2024-09-11 | 6 | 0% | 2024-09-05 | 2024-09-11 | 6 | 100%
Analysis and Design: Data model/data set, Class diagram,Activity diagram, Deployment Diagram | 2024-09-12 | 2024-09-18 | 6 | 0% | 2024-09-12 | 2024-09-18 | 6 | 100%
Wireframe/Algorithm and flow chart/Input form design/Output Report Design | 2024-09-19 | 2024-09-25 | 6 | 0% | 2024-09-19 | 2024-09-25 | 6 | 100%
RMMM Plan, Feasibility analysis and Test case Design | 2024-09-26 | 2024-10-02 | 6 | 0% | 2024-09-26 | 2024-10-02 | 6 | 100%
Review II (on Activity 3 to 13)
Project Report Preparation | 2024-10-03 | 2024-10-09 | 6 | 0% | 2024-10-03 | 2024-10-09 | 6 | 100%
Finalisation of PPT's nad project report with print and guide signature | 2024-10-10 | 2024-10-16 | 6 | 0% | 2024-10-10 | 2024-10-16 | 6 | 100%
Note on C3: ATHARVA: Insert Start Date
Note on G3: ATHARVA: Insert Start Date

## Sem 7
| Project name: | Online Voting System Using Blockchain
| Project Start: | 2024-07-11
| Current Date: | 2024-10-16
| Weeks in Progress: | 14
[5 empty] | 2024-07-11 | 2024-07-18 | 2024-07-25 | 2024-08-01 | 2024-08-08 | 2024-08-15 | 2024-08-22 | 2024-08-29 | 2024-09-05 | 2024-09-12 | 2024-09-19 | 2024-09-26 | 2024-10-03 | 2024-10-10 | 2024-10-17
Task | Start Date | End Date | Days | Progress | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Group Finalization/Domain | 2024-07-11 | 2024-07-17 | 6 | 100%
Topic finalization/Project Name submission | 2024-07-18 | 2024-07-24 | 6 | 100%
Topic finalization/Project Name submission (objectives/problem statement/scope) | 2024-07-25 | 2024-07-31 | 6 | 100%
Literature study & limitation of existing system (refer IEEE/ACM/Springer/Elsevier journal papers) | 2024-08-01 | 2024-08-07 | 6 | 100%
Abstract, Problem statement/scope & objective Finalization. | 2024-08-08 | 2024-08-14 | 6 | 100%
Implementation plan /Timeline chart for sem vii & viii | 2024-08-15 | 2024-08-21 | 6 | 100%
SRS-Functional & Non functional requirements, S/W Engg Model | 2024-08-22 | 2024-08-28 | 6 | 100% | 2024-08-22: 0
Proposed system architecture/flow chart & Analysis & Design: Use Case, DFD-0,Sequence | 2024-08-29 | 2024-09-04 | 6 | 100%
Review I(on Activity 3 to 8)
Reviw Paper Publication (Survey Paper) | 2024-09-05 | 2024-09-11 | 6 | 100%
Analysis & Design: Data model/data set, Class diagram,Activity diagram, Deployment Diagram | 2024-09-12 | 2024-09-18 | 6 | 100%
Wireframe/Algorithm & flow chart/Input form design/Output Report Design | 2024-09-19 | 2024-09-25 | 6 | 100%
RMMM Plan, Feasibility analysis & Test case Design | 2024-09-26 | 2024-10-02 | 6 | 100%
Review II (on Activity 3 to 13)
Project Report Preparation | 2024-10-03 | 2024-10-09 | 6 | 100%
Finalisation of PPT's & project report with print & guide signature | 2024-10-10 | 2024-10-16 | 6 | 100%
Note on C3: ATHARVA: Insert Start Date

## Sem 8
| Project name: | Online Voting System Using Blockchain
| Project Start: | 2025-01-06
| Current Date: | 2025-04-20
| Weeks in Progress: | 15
[5 empty] | 2025-01-06 | 2025-01-13 | 2025-01-20 | 2025-01-27 | 2025-02-03 | 2025-02-10 | 2025-02-17 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14
Task | Start Date | End Date | Days | Progress | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
50%Iimplementation with Database/Algorithm Finalization | 2025-01-06 | 2025-01-12 | 7 | 100%
| 2025-01-13 | 2025-01-19 | 7 | 100%
| 2025-01-20 | 2025-01-27 | 8 | 100%
Review I (on 50% Implementation)
100% Project Completion with Result | 2025-01-28 | 2025-01-31 | 4 | 100% | bar: 2025-01-27
| 2025-02-01 | 2025-02-07 | 7 | 100%
| 2025-02-08 | 2025-02-14 | 7 | 100%
Finalization and Submission of Research Paper | 2025-02-15 | 2025-02-21 | 7 | 100%
| 2025-02-22 | 2025-02-28 | 7 | 100%
Project Report Finalization | 2025-03-01 | 2025-03-07 | 7 | 100%
| 2025-03-08 | 2025-03-14 | 7 | 100%
| 2025-03-15 | 2025-03-21 | 7 | 100%
| 2025-03-22 | 2025-03-26 | 5 | 100%
Review II (on 100% Implementation)
Updation in Project as per remark of Review 4 | 2025-03-29 | 2025-04-04 | 6 | 100%
Updation in Report and Finalization | 2025-04-05 | 2025-04-11 | 7 | 100%
PPT's Finalization | 2025-04-12 | 2025-04-18 | 7 | 100%
Note on C3: ATHARVA: Insert Start Date